# The Order of st george

2022 Business Plan

Table of Contents

Introduction	1

Background to the Business Plan	1

Elements of the Annual Planning Cycle	1

Accountabilities	2

MISSION AND VALUES.............................................................................................................3

Mission .................................................................................................................................3

Vision.................................................................................................................................................3

Belief Statement....................................................................................................................3

Values …………………………………………………………………………………………...….3

Stratgic Objectives................................................................................................................3

KEY RESULT AREAS AND OVERALL OBJECTIVES.............................................................3

Key Result Area 1: Recognition...........................................................................................4

Goals:................................................................................................................................................4

Key Result Area 2: Build Consittuency and Relationships       .....................................................5

Goals.................................................................................................................................................5

Key Result Area 3: Srtengthen Financial Position...................................................................6

Goals:…………..…………………………….………………………………………………..……………..6

Key Result Area 4:.Develop Spevial and Ongoing Prorams ...............................................6

Goals:................................................................................................................................................6

Key Result Area 5: Govern Effectively and Efficvently ........................................................7

Goals....................................................................................................................................7

# Introduction

## Background to the Business Plan

The 2022 Business Plan for the Order of St George (the ORDER) identifies areas of operation and management to be addressed in 2022. These activities are essential to the long-term viability of the ORDER. The Board of Directors has five priorities which guide the 2022 program:

Recognition– International, Domestic and Vice regal

Growth – constituency, membership and branding in the community at large

Financial growth and Sustainability – strategic and tactical

Programs - national and at the Priory level – “building a track record”

Governance – oversight and enablement

These priorities will be achieved through activities focused on ongoing governance renewal, on fund raising, marketing and constituency building, investment in our people and communications

The Board agrees that to be successful, the Order must:

- Build its reputation and recognition as a chivalric order

- build constituency with like-minded organizations and the community at large

- cultivate ongoing donor and community partner relationships.

- engage and expand its membership, that is the Knights and Dames of the Order;

- increase fund raising opportunities and returns on these opportunities; and

- invest in and focus on exemplary governance and accountability

## Elements of the Annual Planning Cycle

The Annual Planning Cycle includes the following elements:

- An environmental review of issues facing the ORDER;

- A review of previous year achievements;

- Identification of initiatives to be undertaken in the coming and subsequent year;

- Business Plan approval and alignment with the annual budget; and

- Performance management at the organizational and Board levels.

## Accountabilities

# The Board of Directors is accountable for preparing the content of the Business Plan and developing and implementing strategies and plans to achieve Key Results. 
1. Mission, Vision, Values Strategic Objectives

MISSION STATEMENT

The Order of St. George is a Chivalric Order which, together with its Charitable Foundation, seeks to better the health and well-being of members of the Canadian Armed Forces, Veterans, and their families, and to support the Canadian Cadet and Junior Ranger Programs.

## VISION STATEMENT

By 2025 The Corporation will grow to 500 members and become a well-recognized and respected international organization that creates a significant difference in the lives of those we serve.

## BELIEF STATEMENT

The Corporation believes it can practice the chivalric virtues of charity, service, and integrity effectively through its Purpose of support and service to those who have provided service to their country and to their community.

## values

We value:

The practice of chivalric virtues of charity, service. and integrity: fill in statement

Transparency and Accountability:  fill in statement

Stewardship of Resources: We pursue due diligence and stewardship in accounting for financial and other assets.

# STRATEGIC OBJECTIVES

## The Strategic Plan identifies the following five (5) strategic objectives:

To be recognized nationally and internationally - The ORDER will be recognized nationally and internationally as a chivalric ORDER that is a respected and trusted supporter of the Canadian Armed Forces, Veterans, their families and Cadet Corps and Junior Ranger programs

Build Constituency and relationships - The ORDER will grow to at least 500 members representing all areas of Canada, re-energize its Knights and Dames for service and the practice of Chivalric values, advance its public recognition (brand) and connect with like-minded individuals and organizations.

Strengthen financial position - The ORDER will create a strong financial position to enable the planning and execution of national programs and local programs within the Priories that further corporate purposes.

Develop special and ongoing programs - The ORDER will develop national programs and programs within the Priories that further the corporate strategic statements of intent with special attention to fulfilling its chivalric values and addressing current needs of its beneficiaries.

Govern the Order effectively and efficiently - The Order will align and improve its governance, administration, and operations by completing the Governance Renewal Project and undertaking a continuous improvement process.

# Key Result Areas

Key Result Areas are those priorities where ORDER must be successful in order to be true to its Mission, Vision and Values. The following are the 2022 Key Result Areas. These Key result Areas are not in any order of priority.

## Key Result area 1: Recognition

Objective: To position the order to gain vice regal recognition, obtain Heraldic recognition; and establish a position within the International Order of St George and other chivalric organizations within Canada.

Goals:

### 1.1  By establishing an ad hoc committee led by the Grand Prior to review Vice Regal and Heraldic recognition requirements; develop and begin the execution of a work plan for fulfilling the requirements; document past track record and ongoing accomplishments; and assess progress to establish best timing for submitting applications,

Accountability: Board and GP

Target Date: Plan and Schedule prepared and approved by 31 May 2022

Performance Indicators:

- Committee established

- Plans complete with tasks and milestones identified

- Quarterly progress reports identifying issues, obstacles and recommendations to Board of Directors.

- Process for identifying past record and tracking ongoing accomplishment at Priory and National levels

1.2  By reviewing the validity of referring to the ‘Grand Priory of Canada and The Americas’ and

advancing connections and a spirit of cooperation with other Grand Priories of the Order of St George, starting with the UK, Europe and USA

Accountability: GP with Priors and Advisory Council

Target Date: Name resolution and connections with UK, Europe and USA established by 31 May 2022

Performance Indicators:

- Resolution of issues related to members/priories located in the USA and connected to the Canadian Corporation

- Connections with UK, Europe and USA in place

1.3  By identifying a suitable and significant Canadian contribution to the international celebration of ORDER’s Septcentennial – 700th Anniversary in 2025

Accountability: Board of Directors and GP

Target Date: 31 December 2022

Performance Indicators:

- Ad hoc committee to lead the planning of the Canadian celebration Plan in place

- Initiatives and budget approved by the Board.

- Execution requirements identified

1.4  By developing connections and a spirit of cooperation with other Canadian chivalric orders.

Accountability: GP, Priors and AC

Target Date: 31 December 2022

Performance Indicators:

- Multiple potential chivalric organizations identified and at least one Canadian relationship established in 2022

## Key Result area 2: build Constiency

Objective: The order will grow numerically and geographically; re-energize its membership and make advancements in public recognition within Canada.

Goals:

2.1    By developing and implementing a Communications Plan to address the who, what, when and how of communications including appropriate use of both official languages in Order communications.

Accountability:   BoD

Target Date: 	30 September 2022

Performance Indicator:

Plan developed and approved; implementation at national and Priory level

2.2    By reviewing communication channels including “round two” of website modernization and the use of other social media

Accountability:

Target Date:

Performance Indicator:    Website has modern look and feel; navigation with minimum clicks; suitable links to Foundation specific site location

2.3    By establishing a new Editor/Editorial Team to produce the Chronicle as is while reviewing reader needs/desires, the Newsletter format, content and frequency to make recommendations for change if necessary.

Accountability: BoD (VChair Lead)

Target Date: 31 May 2022

Performance Indicator: Editor’s ToR developed, mechanism for seeking candidates established and position filled.

  - By connecting with individual members to identify their interests, needs and ideas about the future of the ORDER

Accountability:   Bod (EXCOM?)

Target Date:

Performance Indicator:    Survey?, ???

  - By connecting Field Knights/Dames within Priories and as part of national communications with the view to encouraging them to become members of the Order.

Accountability:

Target Date:

Performance Indicator:    Field Knights/Dames established in separate “list” of Member 365 – added to general distribution list as appropriate.

  - By launching a national recruiting and retention campaign aimed at increasing the number of Postulants per year and retaining current members

Accountability:   Priors Round Table?

Target Date: 	 31 December 2022

Performance Indicator:   A net gain of 70 active members in 2022

2.7  By developing and implementing a continuity plan to ensure seamless transitions when Priors retire and develop individuals who can take on such leadership positions and by focusing on identifying a replacement Prior for the Prairie Priory and new Prior to take on the proposed Quebec Priory.

Accountability:  GP and Priors’ Round Table

Target Date:

Performance Indicator:    New Priors appointed for Prairie and the Proposed Quebec Priories in place. “Assistant Priors” identified as possible replacement Priors for the other Priories.

2.8   By identifying organizations that would be considered “like-minded” and establishing partnerships that will contribute to enhancing the Order’s “brand” in the community.

Accountability:   BoD (Exec Committee?)

Target Date:

Performance Indicator:   Create at least one new partnership

## STRATEGIC OBJECTIVE 3: Strengthen financial position

The ORDER will create a strong financial position to enable the planning and execution of national programs and local initiatives within the Priories that further corporate purposes

3.1 	By reviewing current book keeping practices and improving the timeliness of accounting entries and reporting.

Accountability:  Treasurer

Target Date: 	Report to BoD by May 2022

Performance Indicator: Process reviewed and adjusted as necessary; access to high level accounts as necessary.

3.2	By developing connections with corporate sponsors whose leadership might be interested in becoming Knights/Dames or whose corporate contributions could be directed to both the Order and the Foundation.

Accountability:

Target Date:

Performance Indicator:

3.3	By

Accountability:

Target Date:

Performance Indicator:

STRATEGIC OBJECTIVE 4: DEVELOP SPECIAL AND ONGOING PROGRAMS

The ORDER will develop national programs and programs within the Priories that further the corporate strategic statements of intent with special attention to fulfilling its chivalric values and addressing current needs of its beneficiaries.

4.1   By identifying a national cause or causes that will resonate with the membership and the public.

Accountability:   BOD (Program Committee ? and Priors)

Target Date:

Performance Indicator:  Identify at least one in-year project or an ongoing National program; link the projects/programs undertaken within the Priories to National objectives; develop a listing of Priory events and link these to the national objectives

4.2    By working with the Foundation to develop fundraising agreement templates that govern initiatives that support specific Order/Priory Causes undertaken through the Foundation.

Accountability: BOD (Program Chair and Foundation BoD with Priors’ Round Table)

Target Date: 	 April 2022

Performance Indicator: Policy based Agreement Template developed and implemented.

4.3    By identifying appropriate advocacy and ambassadorship opportunities for members and for corporate partners and implement affordable, achievable, and acceptable initiatives.

Accountability:   BOD – EXCOM Lead

Target Date:  31 Dec 2022

Performance Indicator:  Listing of appropriate advocacy initiatives and process for adding new initiatives in place.

## STRATEGIC OBJECTIVE 5: Govern effectively and efficiently

The ORDER will align and improve its governance, administration, and operations by completing the Governance Renewal Project and undertaking a continuous improvement process.

Key Result Areas

5.1    By approving the Board Committee Structure including Committee ToRs

Accountability: The Board	(Governance Chair/Committee lead)

Target Date:     31 May 2022

Performance Indicator: Committee Structure in place and functional.

  - By completing the 2022 Governance Renewal Project including validation of constating documents, the By-law, completion of the Policy Guidance Manual, committee structure and TORs.

Accountability: The Board	(Governance Chair/Committee lead)

Target Date: 	December 2022

Performance Indicator: Project Deliverables completed, approved and published

5.3     By conducting Board orientation and ongoing training:

Accountability:  Board (Governance Lead)

Target Date:	31 December 2022

Performance Indicator: Directors attend one in-house and at least one outside director training opportunity (seminar/webinar).  Board member orientation package developed and available for new directors.

5.4   By developing/adopting and administering a Board assessment questionnaire:

Accountability:  Board (Governance Chair Led)

Target Date:	31 December 2022

Performance Indicator: Questionnaire developed and administered in 2022 (reporting on 2021) Report delivered to BoD and action items to appropriate committees.

5.5    By developing and executing a Board continuity plan and recruiting new directors with the eye to officer succession planning

Accountability:  Board of Directors

Target Date:	31 May 2022

Performance Indicator:

- Continuity Plan in place

- Policy supporting nomination committee approved; and

- First ad hoc Nominating Committee appointed by Board Chair

- Nominations for new nominate directors and Board officers prior to the June AMM.

Note Canada and the Americas has never been a recognized name for the OstG Corporation in Canada.